## G702 Application
Application and Certificate for Payment
Project |  | 2026-014 — Riverside Medical Office Building
Contract |  | PC-2026-014
Application No. |  | 1
Period |  | 2026-02-01 to 2026-02-28
Application date |  | 2026-02-28
1 | Original contract sum | 4850000
2 | Net change by change orders | 0
3 | Contract sum to date (1 + 2)
4 | Total completed and stored to date
5a | Retainage on completed work | 17350
5b | Retainage on stored material | 0
5 | Total retainage (5a + 5b)
6 | Total earned less retainage (4 − 5)
7 | Less previous certificates for payment | 0
8 | Current payment due (6 − 7)
9 | Balance to finish, including retainage (3 − 6)
Change order summary
| Approved in previous months — additions | 0
| Approved in previous months — deductions | 0
| Approved this month — additions | 0
| Approved this month — deductions | 0
Prepared with Massing Bill. Format follows the AIA G702/G703 line structure. Massing Bill is not affiliated with, endorsed by, or sponsored by The American Institute of Architects. AIA®, G702® and G703® are registered trademarks of the AIA.

## G703 Continuation
Continuation Sheet
2026-014 — Riverside Medical Office Building
Application No. 1 · 2026-02-01 to 2026-02-28
A Item No. | B Description of Work | CSI | C Scheduled Value | D From Previous Application | E This Period | F Materials Presently Stored | G Total Completed and Stored | % (G / C) | H Balance to Finish | I Retainage
001 | General conditions | 01 | 340000 | 0 | 42000 | 0 |  |  |  | 2100
002 | Demolition and site clearing | 02 | 185000 | 0 | 185000 | 0 |  |  |  | 9250
003 | Concrete — foundations and slabs | 03 | 720000 | 0 | 120000 | 0 |  |  |  | 6000
004 | Masonry | 04 | 265000 | 0 | 0 | 0 |  |  |  | 0
005 | Structural steel | 05 | 890000 | 0 | 0 | 0 |  |  |  | 0
006 | Rough and finish carpentry | 06 | 210000 | 0 | 0 | 0 |  |  |  | 0
007 | Roofing and waterproofing | 07 | 305000 | 0 | 0 | 0 |  |  |  | 0
008 | Glazing and curtain wall | 08 | 615000 | 0 | 0 | 0 |  |  |  | 0
009 | Interior finishes | 09 | 430000 | 0 | 0 | 0 |  |  |  | 0
010 | Plumbing | 22 | 275000 | 0 | 0 | 0 |  |  |  | 0
011 | HVAC | 23 | 395000 | 0 | 0 | 0 |  |  |  | 0
012 | Electrical | 26 | 220000 | 0 | 0 | 0 |  |  |  | 0
TOTALS
Prepared with Massing Bill. Format follows the AIA G702/G703 line structure. Massing Bill is not affiliated with, endorsed by, or sponsored by The American Institute of Architects. AIA®, G702® and G703® are registered trademarks of the AIA.

## Reconciliation
Reconciliation
1 warning(s).
Rule | Severity | Finding | Expected | Actual | Difference | Reference
COMPLIANCE-MISSING | warning | Form W-9: nothing on file. |  |  |  | project compliance requirements
INFO-RETAINED | info | Retainage held to date: $17,350.00. |  | 17350
INFO-COMPLETE | info | Project is 7.15% complete by value. |  | 7.15